## Con-Artists
[6 empty] | Enrolment Completed: | 2024-08-07 |  |  | Event | Date | Days from Trial Start | Status | Notes
[6 empty] | Original Topline E | 827-857 Days from Start |  |  | Trial Start | 2022-06-22 | 0 | Actual | Official start
[6 empty] | Current Expect Topline | 1242 Days from Start |  |  | Ideal Enrollment End | 2022-12-19 | 180 | Ideal | 6 months enrollment
[6 empty] | Delay | 415 | 385 | Days | Cohort A Enrollment | 2023-12-10 | 536 | Actual | Announced Dec 2023
|  |  |  | Study Start Actual: | 2022-06-22 |  |  |  |  | Ideal Treatment Complete | 2023-12-19 | 545 | Ideal | 12-month treatment
[10 empty] | DSMB Interim Review | 2024-04-16 | 664 | Actual | Positive futility, promised Q4 2024
[10 empty] | Full Enrollment Complete | 2024-08-07 | 777 | Actual | All 105 patients enrolled
[10 empty] | Ideal Data Release | 2024-03-18 | 635 | Ideal | 3 months post-treatment analysis
[10 empty] | Original Q4 2024 Promise | 2024-11-15 | 877 | Promised | From April 2024 announcement
[10 empty] | CRL Received | 2025-07-11 | 1115 | Actual | Now promises Q3 2025 data
[10 empty] | Revised Q3 2025 Promise | 2025-09-15 | 1181 | Promised | From July 2025 CRL
[10 empty] | Type A Meeting | 2025-09-24 | 1190 | Actual | Now promises mid-Q4 2025
[10 empty] | Today | 2025-11-11 | 1238 | Actual | Still waiting...
[10 empty] | Current Mid-Q4 2025 Promise | 2025-11-15 | 1242 | Promised | Current expectation late q4
[10 empty] | ClinicalTrials.gov Deadline | 2025-12-31 | 1288 | Deadline | "Latest possible date"
Scenario | Peak Sales | EV Multiple | Equity Value | Price/Share | vs. Current
DMD Success(PUL v2.0 passes) | $100-200M | 5-6x | $500-1.2B | $12-28 | +92-348%✓
Cardiac Modest(DMD cardiomyopathy only) | $50M | 3-4x | $150-200M | $3.50-4.65 | -44-56%✗
Cardiac Upside(Dilated cardiomyopathy) | $150M | 4-5x | $600-750M | $14-17.45 | 121.21
Cardiac Home Run(HFrEF) | $300M | 5-6x | $1.5-1.8B | $35-42 | 453.29
Primary Fails(No approval) | 0 | N/A | ~$50M (cash) | $0.50-1.00 | -92-96%✗

## Sheet3
HOPE-2 | ALLSTAR Trial